## Sheet1
No. | Description | Evaluation | Likelihood | Impact Level | Responsibility | Response | Control Measures
1 | Power outage | Computer offline | Low | High | External - Utility provider | Call provider to request fix | Ensure required devices are fully charged
2 | System crash | Work inaccessible | Low | High | Developer | Contact IT services | Adhere to developer professional safety standards, to avoid accidentally causing crash. be sure sites/apps/etc are not suspicious.
3 | Work injury | Slow, inefficient pace | Low | Medium | Developer | Seek appropriate medical attention | Ensure clear desk and work environment, according to health and safety policies, and DSE guidelines.
4 | Broken version deployed | may have missing requirements or issues | Medium | High | Developer | Revert to previous stable version | Ensure tests pass before pushing to repo. Only merge to main once all tests pass and 80% coverage achieved (min 60% for projectCRUD).
5 | Scope creep | deadlines missed | Medium | Medium | Developer | avoid overloading sprints | pay attention to jira board, add and update regularly
6 | Incorrect credentials | database inaccessible | Low | Medium | Developer | input correct credentials in Dbconfig file | ensure db connection can safely be established before writing feature code
7 | assessor can't access application's database | database inaccessible | Medium | High | Developer | send correct details to assessor | ensure there is comprehensive instructions provided with the application, or an SQL file to run that will create the database for the user
8 | functions work incorrectly. | e.g delete removes more than one record/whole table | Medium | High | Developer | Edit functions to give desired output | test function with multiple assertions, checking the database in the MySQL workbench before and after. Could run the function inside workbench first.